## List of Properties
Basis Points/Loan number | Status | Address | Closing | UC $ | Single/Multi | Notified | Secured | Electric ordered | Current List | Starting List Price | Listing Date | Change | Rented | Rent | Lease End
| Hold | 7332 Wellington |  |  | Single | y | y |  | 199900 | 249900 | 2024-05-16
| Active | 3838 Oregon |  | 130K | Single | y | y |  | 129900 | 99900 | 2024-03-19 |  | n |  | n/a
| Hold | 4278 E Sacremento |  |  | 4 Family | y | y |  | 109900 | 149900 | 2024-05-18 |  | y 1 of 4
| Hold | 2359 Michigan |  |  | single | y | y |  | 159900 | 159900 | 2024-10-16
| Active | 5175 Cabanne |  | 40000 | single | y | y |  | 54900 | 69900 | 2024-10-14 | 2025-04-25
loan # 307624 | Active | 5168 Vernon |  |  | single | y | y |  | 89900 | 129000 | 2024-10-30 | 2025-05-19
basis 109,520 loan # 308284 | Under Contract | 4527 Minnesota | 2025-07-08 | 99900 | 2 family | y | y |  | 99900 | 139900 | 2024-12-10 | 2025-04-25
| Active | 3936 Lexington |  |  | duplex | y | y |  | 54900 | 79900 | 2024-11-19 | 2025-05-25
| Active | 3735 Wisconsin |  |  | 4 family | y | y |  | 139900 | 199900 | 2024-12-10 | 2025-05-25
loan # 307232 | pre | 2131-2133 Stansbury St |  |  | 2 family | y | y |  | 199900
| Active | 1603 Belleau Lake Dr O'Fallon |  |  | single | y |  |  | 89000 | 129000 |  | 2025-05-25 | n
220k | pre | 3539 Michigan 220k Jason |  |  | 4 family | [7 empty] | y | 600
loan #304975 basis $90,177.49 | Active | 4369 Evans St Louis 66113 |  |  | single | y | y |  | 59900 |  |  | 2025-05-25 | n
| Under Contract | 10533 Earl Dr | 2025-07-02 | 99900 | single | y | y |  | 99000
loan # 306994 basis $101,675 | Under Contract | 3929 Pennsylvania | 7/16 or before | 111650 | 2 family | y | y |  | 119900 | 119900
loan # 305065 basis $244,076 | Under Contract | 7280 S Roland | 2025-07-11 | 265000 | single | y | y |  | 279900 | 299900 |  | 2025-06-15
loan #304061 basis $158,242 | pre | 3708 Bamberger Ave 63116 |  |  | single | y
loan #307748. basis $77,787 | pre | 3223 Taft 63111 |  |  |  | y

## 3709 Bamberger
PreList | List | Under Contract
6/11 Jake will have Paul rekey
Code is 3030, Paut to clean out mold/remove flooring in basement

## 3929 Pennsylvania
Prelist | List | Under Contract
listing agreement for 119,900 signed by Mike 6/10

## 7280 S Roland
PRELIST | LISTING | UNDER CONTRACT
3/6 requested rekey | was listed previously in current condition for 304,900
3/16 checked on rekey | started at 324,999, 60 days OM not under contract
3/16 confirmed rekey, schedule photos for 3/18 | Listing photos scheduled for 4/10

## 10533 Earl Dr
PRELIST | LISTING | UNDER CONTRACT
received 1/29, sent to Kevin to rekey | Listed 119,900
Tenant occupied, currently paying 1200 | Price change 3/24
Jason working on tenant prior to list
2/4 sendn listing agreement for 119,900
tenant occupied new lease for $1500 per month
schedule photos with Jason for Tues 2/11

## 1603 Belleau Lake
PRELIST | LISTING | UNDER CONTRACT
find out from County staus re flood | https://matrix.marismatrix.com/matrix/shared/tm67YtgDssHd/1603BelleauLakeDr
Per Kevin list at 129k, listing agreement sent to Mike | listed 129,000
got info from County, as well as documents from previous owner | price drop to 109,900
Walked property 2/2 for photos, | next price drop 3/25

## 3735 Wisconsin
PRELIST | LISTING | UNDER CONTRACT
https://drive.google.com/drive/folders/1TO2QhFChToFDTXInRMFOCOi8svE99IlU?usp=sharing | https://matrix.marismatrix.com/matrix/shared/9rr7LgdbdsHd/3735WisconsinAve
Current list 179,900
next change 3/22

## 3936 Lexington
PRELIST | LISTING | UNDER CONTRACT
https://drive.google.com/drive/folders/1dSviyXWJZxsvYJ2CGmBaTLX-xCv7uH1W?usp=drive_link | https://matrix.marismatrix.com/matrix/shared/MlmYl3WvcsHd/3936LexingtonAve
current list 74,900
next price change 2/22

## 4527 Minnesota
PRELIST | LISTING | UNDER CONTRACT
list to sell as-is until Paul is done with Sacremento | https://matrix.marismatrix.com/matrix/shared/pj1zKsStcsHd/4527MinnesotaAve
Paul to update to occupancy standards and place tenant in unit | listed 119,900
https://drive.google.com/drive/folders/1-JkbATUXbSlSXVolW9W2XBfOm4gi1oKJ?usp=drive_link | next price change 3/22
Paul did cleanout of the building
slope
4/17 Found property had lockboxes stolen, can't enter, also condenser coil has been stolen,
Approved Paul to rekey again tomorrow
4/18 Chip reported the neighbor said there are squatters on the second floor, sent message to Paul

## 5168 Vernon
PRELIST | LIST | UNDER CONTRACT
5168 Vernon | current list 109,900
https://matrix.marismatrix.com/matrix/shared/5SBx50wZcsHd/5168VernonAve

## 7327 Pennsylvania
PRELIST | LIST | UNDER CONTRACT
https://drive.google.com/drive/folders/1BxjTAh1PfWGwz7SVii_tinl0lTvbHE8r?usp=drive_link | https://matrix.marismatrix.com/matrix/shared/YyNhLJB0csHd/7327PennsylvaniaAve | 140000
NEED LBP
Earnest due 1/21
Financing 2/7
Close 2/12
SOLD

## 5175 Cabanne
PRELIST | LIST | UNDER CONTRACT
https://drive.google.com/drive/folders/1Id1sa561CHbBuFjO1BMEQWKnwFOYauFz?usp=drive_link | Current list 64,900
-When Paul is done with
Sacremento he will box in
https://matrix.marismatrix.com/matrix/shared/ffsZhWK2csHd/5174CabanneAve

## 2359 Michigan
PRELIST | LISTING | UNDER CONTRACT
Chikkas rehabbing
need outdoor living space plan
March list plan
https://drive.google.com/drive/folders/171hMhBa7IR_RFUP6U2_bSP9L6cc4-clv?usp=drive_link

## 2104 Harris
PRELIST | LIST | UNDER CONTRACT
https://drive.google.com/drive/folders/1gbo7f7C-UVZ_IdwWxw0YlyNjitHMHlc-?usp=drive_link | 39900
https://matrix.marismatrix.com/matrix/shared/vYc2gFP3csHd/2104HarrisAve

## 3539 Michigan
PRELIST | LIST | UNDER CONTRACT
Jason working eviction
Need CMA for sale
Quad 1 bed units
Emailed Jason re evictions 2/13
4/18 emailed Jason for access on Tues 11-1
4/18 emaied Jason for leases and rental verification
4/19 Jason confirmed access for Tues for 2 rented units
4/19 Jason called, no gas on due to a gas leak, asked if
he should install electric WHs or fix gas leak, I said fix the leak, he
wasnt able to reach Kevin.

## 4369 Evans
PRELIST | LISTING | UNDER CONTRACT
requested rekey for after 1/25 | list for 79,900
basis 90,178 | https://portal.onehome.com/en-US/share/1140326R55624
Listed currently, agent contacted | 69,900 4/25
https://portal.onehome.com/en-US/share/1128261s07060
2/13 need photos then list mls

## 2619 Ann
PRELIST | LISTING | UNDER CONTRACT
https://drive.google.com/drive/folders/1le1spmPgJlw1OokwsfTzIOy-gcjXvSBk?usp=sharing | https://matrix.marismatrix.com/matrix/shared/B35lV7S4csHd/2619AnnAve | UC 1/26
Earnest 1/31
Inspections 2/10
Financing 2/14
Close 2/21
Need LBP from buyer-requested
Inspection scheduled 1/28
Per Buyer agent expect Mutual Release 1/29

## 11709 Talbott
PRELIST | LIST | UNDER CONTRACT
https://drive.google.com/drive/folders/18mqnWW4fb8xS9YmvF8Ibqt261oWvOi3f?usp=drive_link | list 149,900 1/22
sign in yard
Offer 1: counter at 140k, on 1/27 or remove
buyers agent commission
-countered, buyers highest and best is 135k with
commission or 131,355
https://matrix.marismatrix.com/matrix/shared/HJv9lNX5csHd/11709TalbottCt
Kevin approved offer of 135k, sent to Mike for signature 1/28 3;30PM

## 3414 Regal
PRELIST | LISTING | UNDER CONTRACT
| https://matrix.marismatrix.com/matrix/shared/m1mTW247csHd/3414RegalPlace | Close 2/14
Inspections Resolved
Loan Contingency 2/5

## 7332 Wellington
PRELIST | LIST | UNDER CONTRACT
Ian to rehab | 330-360 range ARV
Listing on Hold
week of 1/20 get updated timeline from Ian
Site visit 4/7 MEPs not completed to passing, timeline for project 10 weeks out
text to Ian 4/17 to check on permitting
. -reply that electric passed, HVAC will be this friday, Plumbing still an issue
Spoke to Ian about reframing the project to bring in a plumber, getting the
plumbing to pass is too much for him
Per Ian HVAC and Electric passed, stil struggling with plumbing, sent message to
Kevin to possibly reframe the project
Ian messaged back that he is going to try one more time to get plumbing to pass

## 4278 East Sacramento
PRELIST | LIST | UNDER CONTRACT
4 Family, Paul to rehab | Determine list price ARV
1/20 Paul almost finished with 2 units, will put tenants in | list 199,900
then move to other 2 units
1 2 bed unit and 3 1 bed units
Verify Beds/baths with Paul, one unit has kitchen in basement
No furnace, baseboard heat installed and tenants to supply AC
1 Unit Occupancy Inspection 1/28 then place tenant
Unit with kitchen in basement needs clearing of trailer and repair of back
porch to pass occupancy by 2/2/2025
4/18 Per Paul still waiting for electric in 2 new units
repairs needed post tornado per Paul 7/1 should be done next week

## 2110-2112 Harris
PRELIST | LIST | UNDER CONTRACT
https://drive.google.com/drive/folders/1EO8b3FWCdX-SogkfpUgz3A_fyK2NQCtm?usp=drive_link | Current list $54,900 next change 2/22 | closed for 33k 4/3
https://matrix.marismatrix.com/matrix/shared/k0tgrD88csHd/2110HarrisAve

## 2131-2133 Stansbury
PRELIST | LISTING | UNDER CONTRACT
https://drive.google.com/drive/folders/1k0nPSvL62i9OmKKxCdlE18ncSJrWAxTY?usp=drive_link | Per Kevin list for 199,900
Walked with Calvin for Bid to finish to occupancy standards the vacant unit
Tenants had changed locks saying was was broken into, instructed Calvin to change locks again | 2 4 bed 2 bath units
Put lockbox on the property and left the keys the tenant gave me in it, Calvin to switch keys when he | Need to get listing photos of finished side
rekeys it | as well as unfinished side
Need CMS for property as is and as finished rented unit
1/27 Calvin will change the locks today, asked if he should include cleanout in the bid,
I said yes but include it as a separate line item. He asked if we have a budget and I said the cheapest
possible to get us passing occupancy
He has been paid ACH previously, wants to change the bank account so I will send him a new ACH
form to fill out.
FInd out from Jason what rent is currently
CMA
Calvin has sent the bid to Kevin
Calvin provided W-9 on 2/3, has not received ACH but Kevin sais a paper check was mailed
Tenant to remove dogs and prepare their unit for photos by the 17th
Starting eviction process
3/25 sent email to Jason asking for update
4/19 Sent email for update of eviction
5/5 Eviction court date
6/2 Per Jason eviction to be executed this week
WRIT for final eviction set for 6/20, then will clear and clean it to list, may need ozone

## 3838 Oregon
PRELIST | LIST | UNDER CONTRACT
Geraldo to rehab | Listed 129,900
Expected finish 2/1
TASK walk rehab Fri 1/24 to assess
NOTE project over budget due to Duct, assessing city requirement of new waterline
and city requirement to replace framing
Site visit 4/17, projected to be complete 4/31, sent email with project questions

## Process
DAY 1
Drive By
Take Pictures
If tenant occupied get contact info, explain the property has a new owner and say they will be contacted by the owner
Have locksmith change locks
use local, bill Trident, use code 1769, expect to pay 300-500 per property
WITHIN 1 WEEK
Written sales plan that includes BPO (RPR report)
Listing agreement for 180 days
List Property
EVERY 30 DAYS
Drop price by 10k after approval
Asses for sales strategy change (rehab, lease, etc)